## General Mailing Backdater
General Mailing Backdater
Action | Responsible | Additional Participants | Date Due | Notes
Content concept meeting | Director of Development |  | 4 months out from drop date | In whose voice? What pieces are included? Who is the audience? How many segments? What's the call to action? By when?
Draft content--letter, remit, outer envelope, inserts, pledge cards, etc. | Director of Annual Giving |  | 3.5 months out from drop date
Content edits |  |  | 3 months out from drop date | Key for effective backdating--who/how many need to edit this contnet?
Check that initial or final mailing deadline does not fall on a postal holiday | Director of Annual Giving |  | As soon as you are aware that the mailing is needed
Adjust the deadline if it falls on a postal holiday | Director of Annual Giving |  | As soon as you are aware that it falls on a holiday
Complete and submit list request | Director of Annual Giving |  | 2 weeks before print date
Gather mailing list from database manager | Director of Annual Giving |  | 1 weeks before print date
Check ink, paper, and postage | Development/Department Assistant | Office Manager | 2 weeks before print date | Check meter ink in addition to printer ink.
If items need ordered, be sure you can get a company credit card | Development/Department Assistant |  | 1 week out before print date | Supervisors are frequently out of the office and these supplies can be very expensive.
Reorder/restock ink, paper, and postage as needed | Development/Department Assistant | Office Manager | 1 week before print date | Be mindful of the office manager's ordering schedule.
Print materials for mailing | Development/Department Assistant | Printer if it's going out | 2 days before assembly and mailing
Schedule volunteers to help with mailing | Director of Annual Giving |  | 1 week before assembly and mailing | Be respectful of their time. If you told them they were needed, give them something meaningful to do even if there is a hiccup with our process.
Other items to consider and factor into your schedule
Do you need signatures for your mailing? | Director of Annual Giving |  | as soon as items are printed | Send a signing date as a calendar appointment.
Note on B2: This varies based on the size/structure of your organization -Kristi Howard-Shultz